## 1. README
MIRAI TECHNOLOGIES (miraitechnologies.net) — SEO ISSUES & DEVELOPER FIX WORKBOOK
Prepared by errorr.in ¦ Audit date: 16 July 2026 ¦ Method: live crawl of homepage, /products, /about, product detail, city page, /blog + Google index checks
HOW TO USE THIS WORKBOOK
Sheet 2 — Issues Master | Every issue found, with evidence, impact and priority. Filter by Priority or Status. This is the single source of truth.
Sheet 3 — Developer Fixes | Implementation spec per issue: what to change, how, and the acceptance test that proves it is fixed. Work top-down by priority.
Sheet 4 — Redirect Map | Legacy .php URLs to be 301-mapped. Yellow cells = fill in from Google Search Console before implementing.
Sheet 5 — Metadata Fixes | Current vs proposed title tags, meta descriptions and H1s for the pages sampled. Apply the same rules to all pages of that template.
Sheet 6 — Schema Checklist | Required JSON-LD per template. Static HTML fetch cannot verify JS-injected schema, so every row must be validated with Google's Rich Results Test.
Sheet 7 — Verification Tasks | Items that could not be confirmed remotely (robots.txt, sitemap, GSC coverage). Developer to run these checks and update Status.
PRIORITY DEFINITIONS
P0 — Critical | Blocks or damages indexation/rankings site-wide. Fix within 1 week.
P1 — High | Materially hurts rankings, crawling or click-through. Fix within 2–3 weeks.
P2 — Medium | Quality, trust and consistency issues. Fix within 30–45 days.
PASS | Checked and working correctly — no action needed, listed so you know it was audited.
STATUS VALUES (developer updates the Status column as work progresses)
Confirmed | Issue verified in live HTML during this audit.
Needs verification | Could not be confirmed remotely; run the check described in Sheet 7 first.
In progress / Fixed / Won't fix | Developer-updated states.
CONTEXT THE DEVELOPER MUST KNOW
1. | The site is a React SPA with pre-rendered/SSR HTML now live (confirmed on all sampled routes). SSR/prerender parity is a standing hard requirement: every meta tag, canonical, schema block and body content must exist in the server-delivered HTML, not only after hydration.
2. | The old PHP site's URLs (e.g. /brands.php) are still in Google's index under www.miraitechnologies.net with stale titles. Redirects exist (brands.php 301s to /about) but the full legacy URL set must be mapped and monitored in GSC until it drops out of the index.
3. | Do not remove or noindex any /products/*, /product/*, /blog/* or /electronic-component-distributor-in-* URL without checking the Redirect Map sheet first.
ISSUE COUNTS
P0 — Critical | 5
P1 — High | 8
P2 — Medium | 8
PASS (audited OK) | 2

## 2. Issues Master
ID | Category | Scope / Example URL | Issue | Evidence (found during audit, 16 Jul 2026) | Priority | SEO Impact | Status
SEO-01 | Indexation / Legacy site | www.miraitechnologies.net/*.php (site-wide) | Legacy PHP URLs from the old website are still in Google's index, under the www host, showing the old brand title ('Igniting Innovation, Driving Excellence…'). | Google search surfaced www.miraitechnologies.net/brands.php with the old site's title and content in its cached snippet. Fetching it 301-redirects to https://miraitechnologies.net/about — so redirects exist, but Google has not yet refreshed/dropped the stale entries, and the redirect target (/about) is a weak topical match for a brands/products page. | P0 | Stale results dilute brand SERP, split signals between www and non-www, and legacy URLs may be soaking up crawl budget. Until the old URLs are recrawled, they compete with the new pages. | Confirmed
SEO-02 | Host canonicalization | www vs non-www, http vs https (site-wide) | www/non-www and http/https consolidation must be verified for ALL paths, not just the homepage. | New site canonicals all point to non-www https. But the indexed www .php page proves Google historically crawled the www host. Every combination (http://www, https://www, http://) must 301 in a single hop to https://miraitechnologies.net equivalent. | P0 | Split host signals halve link equity and create duplicate-content ambiguity. | Needs verification
SEO-03 | Crawlability | https://miraitechnologies.net/robots.txt | robots.txt could not be confirmed. Must exist, must reference the XML sitemap, and should disallow /cdn-cgi/ (Cloudflare email-protection URLs found linked in page HTML). | City pages link email addresses to /cdn-cgi/l/email-protection (Cloudflare Scrape Shield). These utility URLs are crawlable links in the HTML. | P0 | A missing/misconfigured robots.txt during a replatform is the classic cause of re-indexation failure; /cdn-cgi/ URLs waste crawl budget. | Needs verification
SEO-04 | Indexation | https://miraitechnologies.net/sitemap.xml | XML sitemap existence, completeness and GSC submission unverified. Must contain ALL canonical URLs: homepage, 7 category pages, ~85 product pages, all city pages, 20 blog articles, about, contact, market-area. | Site was previously stuck at ~2 indexed URLs due to the empty React shell. Now that HTML is pre-rendered, a complete sitemap + GSC resubmission is the fastest path to full re-indexation. | P0 | Without a submitted sitemap, re-indexation of 130+ URLs after the SSR fix will be slow and partial. | Needs verification
SEO-05 | Structured data | All templates | Schema markup (JSON-LD) could not be detected in static HTML — but static fetch strips script tags, so this needs Rich Results Test validation per template. Product pages have price (₹195), MOQ, stock status and FAQs sitting in plain HTML — all unusable by Google unless marked up. | Product page /product/mosfet-transistor/irfp4668 shows price, stock, MOQ, GST, FAQs in body text. No schema was verifiable via fetch. Requirement: Organization (site-wide), Product+Offer (product pages), FAQPage (product + city pages), BreadcrumbList (all), BlogPosting (articles), LocalBusiness (contact/city hub). | P0 | No Product schema = no price/stock rich results; no FAQPage = no AEO/AI-answer eligibility. This is the single biggest missed CTR lever on the site. | Needs verification
SEO-06 | URL architecture | /product/* paths | Product detail URLs use THREE inconsistent category path variants: /product/integrated-circuit/…, /product/integrated-circuits/… (plural) and /product/ic/… — for products in the same category. | From /products catalog: LM358L-D08-T sits at /product/integrated-circuit/lm358ld08t while SN74HC541DWR sits at /product/integrated-circuits/sn74hc541dwr and NSIP83086CD sits at /product/ic/nsip83086cd. Category hub pages use singular /products/integrated-circuit. | P1 | Splits topical clustering, creates messy crawl paths, and guarantees future duplicate-URL bugs. One canonical pattern must be enforced with 301s from the variants. | Confirmed
SEO-07 | URL architecture / taxonomy | /product/* categorization | Products are filed under wrong categories in the URL path, breaking topical relevance. | Examples from /products: L7824CV (a linear voltage regulator) under /product/mosfet-transistor/; CD4051BE (analog multiplexer) under /product/mosfet-transistor/; 20D511K (varistor) under /product/mosfet-transistor/; LM2596/LM2576 regulators under /product/transistor/; Si2302 (a MOSFET) under /product/integrated-circuits/; MB6S bridge rectifier under /product/integrated-circuits/. Meanwhile the /products/voltage-regulator category page has almost no products actually pathed to it. | P1 | Category pages lose the SKUs that should reinforce them; regulator category is starved of its own products. Weakens the exact topical-cluster strategy the category descriptions were written for. | Confirmed
SEO-08 | Duplicate content | /product/transistor/lm2596r5 and /product/transistor/lm2596r5v2 | The same part (LM2596R-5) exists as two separate product URLs. | Catalog lists 'LM2596R5 — LM2596R-5.0 5V Step-Down Regulator' and 'LM2596R5v2 — LM2596R-5 5V Buck Converter IC' as distinct pages. | P1 | Classic duplicate content: the two pages cannibalize each other for 'LM2596R-5 buy India' queries. Merge into one URL, 301 the other. | Confirmed
SEO-09 | Metadata generation bug | Product + city page templates | Title tags and meta descriptions are hard-truncated mid-word/mid-value by the template. | Product page IRFP4668: meta description ends 'Rds(on)=3..' (value cut); title ends '…130A, Rds ¦ Buy India' ('Rds' cut mid-spec). City page Bengaluru: meta description ends 'email sales@miraitec...' (email cut mid-address). | P1 | Truncated snippets look broken in SERPs and kill CTR; a cut email address in the description actively misinforms. Truncation must respect word boundaries and drop trailing fragments. | Confirmed
SEO-10 | On-page / template | Homepage, /about (likely all non-city templates) | H1 duplicates the full title tag verbatim — including the pipe and brand suffix. | Homepage H1: 'Buy Electronic Components Online India ¦ Mirai Technologies'. /about H1: 'About Mirai Technologies ¦ Authorized Semiconductor Distributor'. H1s should be clean human-readable headings, not title strings. | P1 | Pipe-and-brand H1s read as machine-generated (quality signal), waste H1 keyword focus, and signal the template renders one field into two slots. | Confirmed
SEO-11 | Internal linking | /products, /blog, /product/* templates | Main navigation is inconsistent: 'Market Area' link present on homepage, /about and city pages, but MISSING from /products, /blog and product detail pages. | Nav on /products and /blog: Home ¦ About ¦ Products ¦ Blog ¦ Contact. Nav on homepage: includes Market Area. | P1 | The market-area hub (and 100+ city pages behind it) loses site-wide internal link equity from the deepest, most numerous templates (products). Inconsistent nav also fragments crawl paths. | Confirmed
SEO-12 | Crawlability / E-E-A-T | City pages + anywhere email appears | Cloudflare email obfuscation replaces the real email with '[email protected]' in served HTML, linking to /cdn-cgi/l/email-protection. | Bengaluru city page: all email mentions render as '[email protected]' to crawlers (and to AI search engines). The real address never appears in crawlable HTML. | P1 | Search engines and AI answer engines cannot extract the business email — hurts NAP consistency, LocalBusiness schema validation and AEO citation. Expose the email in schema (ContactPoint) and/or disable Scrape Shield on key pages. | Confirmed
SEO-13 | Content integrity | /products vs category descriptions | Contradictory inventory claims: /products header says '83+ genuine electronic components' while its own category blurbs claim 279+ ICs, 118+ MOSFETs, 181+ IC chips, 135+ components etc. (sums to 800+). | Both statements appear on the same /products page. Actual products listed in the catalog: ~85. | P1 | Contradictions on the same page undermine trust for both users and quality raters, and inflated counts adjacent to real counts look like manipulation. Pick one truthful number per scope. | Confirmed
SEO-14 | Content quality / E-E-A-T | /blog (all 20 articles) | Every blog article shows the same publish date (2026-06-10) and no author bylines. | All 20 listed articles: 'Published: 2026-06-10'. No author names, bios or dateModified anywhere on the blog index. | P2 | Identical bulk-publish dates are a scaled-content footprint; missing authors is an E-E-A-T gap for YMYL-adjacent procurement advice. Add authors + stagger dateModified as articles are genuinely updated. | Confirmed
SEO-15 | Metadata hygiene | Site-wide templates | Obsolete meta keywords tag present with an identical boilerplate string on every page. | Same keyword string found verbatim on /products, product detail and /blog pages. | P2 | Zero ranking value; identical boilerplate across templates is a low-quality template smell. Remove the tag. | Confirmed
SEO-16 | Brand consistency | City page titles | Brand rendered as 'Mirai Tech' in city page titles but 'Mirai Technologies' everywhere else; city title also drops the word 'Electronic' from the target keyword. | Bengaluru title: 'Component Distributor in Bengaluru ¦ Mirai Tech' vs H1 'Electronic Component Distributor in Bengaluru — Power MOSFETs, IGBTs & ICs'. Target query is 'electronic component distributor in bengaluru'. | P2 | Title/H1/keyword misalignment on the highest-intent local template; inconsistent brand string weakens entity recognition. | Confirmed
SEO-17 | NAP consistency | Product pages vs city pages | Two different phone numbers in use: +91 79429 64662 (WhatsApp CTA on product pages) vs +91 93213 98188 (city pages, all mentions). | IRFP4668 page WhatsApp link uses 7942964662; Bengaluru page repeats 93213 98188 five times. | P2 | If both are real lines, fine — but both must appear in Organization/LocalBusiness schema and stay consistent per purpose. If one is stale, it's a NAP conflict hurting local trust signals. | Confirmed
SEO-18 | Rendering hygiene | Most templates | Leftover app-shell text leaks into the pre-rendered HTML: a stray duplicate 'Mirai Tech' string and 'Loading premium experience...' render as page content. | Present at the bottom of homepage, /about, product and city page HTML. Absent on /products and /blog. | P2 | Junk strings in the indexable body are a quality-signal blemish and can appear in snippets. Exclude loader/shell markup from the prerendered output. | Confirmed
SEO-19 | Rendering parity | All routes | Hydration parity must be verified: the client-side React app must render the same content (and not remove/replace meta tags) as the pre-rendered HTML, on every route type. | Pre-render confirmed on 6 sampled routes (home, about, products, product detail, city, blog index). Blog article pages and market-area hub not yet sampled. | P2 | If hydration swaps titles/canonicals or content diverges, Google may index the post-JS version and reintroduce the original SPA problem. | Needs verification
SEO-20 | Internal linking | Product detail template | Product pages are internal-link dead-ends: only one category link out, no breadcrumbs, no related-products block. | IRFP4668 page links only to its category, nav and an external Infineon datasheet PDF. | P2 | ~85 SKU pages fail to pass equity sideways to related SKUs and give crawlers no lateral paths. Add breadcrumb + 4–6 related parts per page. | Confirmed
SEO-21 | Performance | Site-wide | Core Web Vitals unmeasured post-relaunch; the 'premium experience' hydration loader suggests a heavy JS bundle on top of the prerender. | Not measurable via static fetch. Needs PageSpeed Insights / CrUX check on homepage, one product page, one city page (mobile). | P2 | LCP/INP regressions from hydration are common in prerendered SPAs; India-mobile audience makes this material. | Needs verification
SEO-22 | Canonicals | Sampled pages | Canonical tags present, self-referencing, https non-www on every sampled page. | Verified on all 6 sampled routes. | PASS | Working as intended. | Confirmed
SEO-23 | City page content | City template | City pages have genuinely substantial, differentiated content with FAQs, product portfolio, nearby-city links and category cross-links. | Bengaluru page reviewed in full. | PASS | Strong template — the schema (SEO-05) and title fix (SEO-16) will let it perform. | Confirmed

## 3. Developer Fixes
Issue ID | Priority | Fix Specification (what to build/change) | Implementation Notes | Acceptance Test (definition of done) | Est. Effort
SEO-01 | P0 | Build a complete legacy-URL 301 map. Pull every legacy .php URL from GSC (Indexing > Pages, plus Settings > Crawl stats) and server logs; map each to its closest-topic new URL (see Sheet 4). Re-point brands.php to /products (not /about). | Redirects must be server-level 301 (Cloudflare rule or origin config), single hop, preserving host consolidation. After deploying, use GSC URL Inspection > Request Indexing on the top 10 legacy URLs to accelerate refresh. | site:www.miraitechnologies.net returns 0 legacy .php results within 4–6 weeks; every URL in Sheet 4 returns a single 301 to a 200 page (test with curl -IL). | 0.5–1 day
SEO-02 | P0 | Enforce host canonicalization: 301 http://miraitechnologies.net, http://www…, https://www… (all paths, including .php) to https://miraitechnologies.net/<path> in ONE hop. | Do this at the edge (Cloudflare redirect rules) so it applies before the app. Watch for double-hop chains (www→non-www→https). | curl -IL on 4 host variants × 3 sample paths = 12 tests, each exactly one 301 then 200. | 0.5 day
SEO-03 | P0 | Create/verify robots.txt at the root: allow all main content; Disallow: /cdn-cgi/; Sitemap: https://miraitechnologies.net/sitemap.xml line included. | Do NOT disallow /product/ or JS/CSS assets. Keep it minimal. | https://miraitechnologies.net/robots.txt returns 200, contains the sitemap line and /cdn-cgi/ disallow; GSC robots.txt report shows no errors. | 1 hour
SEO-04 | P0 | Generate a complete XML sitemap (auto-regenerating on build/deploy) containing every canonical 200 URL: ~130+ pages. Submit in GSC. Exclude redirected/duplicate variants (see SEO-06/08). | If page count grows past a few thousand later (more cities/SKUs), move to a sitemap index split by type (products / cities / blog). | Sitemap validates in GSC with 0 errors; 'Discovered - currently not indexed' count trends down weekly; indexed pages climb toward full coverage in 4–8 weeks. | 0.5–1 day
SEO-05 | P0 | Implement JSON-LD in the SERVER-RENDERED head per template: (a) Organization + WebSite on all pages; (b) Product + Offer (price INR, priceCurrency, availability, MOQ via eligibleQuantity, seller) on product pages; (c) FAQPage on product + city pages (FAQs already exist in HTML — mark up the same Q/As); (d) BreadcrumbList on all; (e) BlogPosting with author + datePublished + dateModified on articles; (f) LocalBusiness with real email + both phone numbers on contact + market-area. | See Sheet 6 for field-level spec. JSON-LD must be in the prerendered HTML, not injected post-hydration only — Google's first-pass HTML must contain it (standing SSR requirement for this site). | Every template passes Google Rich Results Test with 0 errors; GSC Enhancements reports appear for Products, FAQs and Breadcrumbs within 2–4 weeks. | 2–3 days
SEO-06 | P1 | Standardize product URLs to ONE pattern: /product/<category-singular>/<sku>. 301 all /product/integrated-circuits/* and /product/ic/* variants to their /product/integrated-circuit/* equivalents. Update every internal link (catalog page, category pages, related links) to emit only the canonical pattern. | Enforce with a route-level redirect + a lint/test in the build that fails if a non-canonical product path is generated. | Crawl of /products yields zero links to plural or /ic/ variants; old variant URLs 301 correctly; sitemap contains only canonical pattern. | 1 day
SEO-07 | P1 | Fix product categorization in the data source: move L7824CV, LM2596R-5, LM2576T-ADJ → voltage-regulator; CD4051BE, MB6S, 20D511K, CD4001BE, HEF4081BP → their correct categories; Si2302 → mosfet-transistor. 301 each moved URL to its new path. | Audit all ~85 SKUs against category in one pass (the catalog Excel from earlier engagements can seed this). The voltage-regulator category page must end up owning its regulators. | Each category page lists only on-topic SKUs; every moved SKU's old URL 301s to the new one; no 404s in GSC after 2 weeks. | 1 day
SEO-08 | P1 | Merge duplicate LM2596R-5 pages: keep the stronger URL, merge unique content, 301 /product/transistor/lm2596r5v2 → the kept URL (which after SEO-07 lives under voltage-regulator). | Check GSC for which of the two currently gets impressions; keep that one's content depth. | One LM2596R-5 page remains; duplicate 301s; site search / catalog lists it once. | 2 hours
SEO-09 | P1 | Fix the metadata generator: truncate titles at ~60 chars and descriptions at ~155 chars on WORD boundaries, never mid-token; never truncate inside an email, number or spec value; drop the trailing fragment and end on a complete clause. | Better: build titles/descriptions from structured fields (part no. + top spec + 'Buy Online India ¦ Mirai Technologies') so length is controlled by construction, not truncation. Regenerate all product + city metadata after the fix. | No title or description on any page ends mid-word, mid-value or mid-email (scripted check across sitemap URLs). | 0.5–1 day
SEO-10 | P1 | Decouple H1 from title tag in the template: H1 = clean page heading without '¦ Brand' suffix. Homepage H1 e.g. 'Buy Genuine Electronic Components Online in India'; /about H1 e.g. 'About Mirai Technologies'. | One-line template change + per-page heading field. See Sheet 5 for proposed strings. | No H1 on the site contains a pipe character or duplicates the title verbatim. | 2 hours
SEO-11 | P1 | Make the navigation identical on every template — include 'Market Area' in the header nav site-wide. | Single shared nav component; the products/blog templates are currently using a different nav variant. | Nav is byte-identical across home, products, product detail, blog, city and about templates. | 1 hour
SEO-12 | P1 | Expose contact email to crawlers: add real email in LocalBusiness/ContactPoint JSON-LD (schema is not obfuscated by Cloudflare), and either disable Scrape Shield email obfuscation for the site or render the email via a method that leaves schema intact. | Keeping visual obfuscation is acceptable IF the schema carries the real address. Verify the prerendered HTML's JSON-LD shows the full email. | Rich Results Test on a city page shows the real email in ContactPoint; no '[email protected]' strings in schema. | 2 hours
SEO-13 | P1 | Reconcile inventory numbers: decide the truthful figure per scope (e.g. '85+ stocked part numbers across 800+ orderable line items' if that's real) and apply consistently on /products header and category blurbs. | This is a content decision for Akshat + client; dev applies the final strings. Do not ship contradictory numbers on one page. | No page states two conflicting totals; numbers match what the catalog actually lists or is verifiably true. | 1 hour + content decision
SEO-14 | P2 | Add author bylines (name, role, short bio) and dateModified to blog articles; update dates only when content genuinely changes. | Create 1–2 real author entities (e.g. sourcing desk lead) reused across posts, with an author page. Feed into BlogPosting schema (SEO-05e). | Every article shows author + published + modified; author page exists and is linked. | 1 day
SEO-15 | P2 | Remove the meta keywords tag from all templates. | One-line template deletion. | No page source contains <meta name="keywords">. | 15 min
SEO-16 | P2 | City title template: 'Electronic Component Distributor in {City} ¦ Mirai Technologies' (fits ~60 chars for most cities; for long city names drop the brand, never the keyword). | Aligns title with H1 and target query; fixes 'Mirai Tech' brand inconsistency in the same pass. | All city titles start with 'Electronic Component Distributor in' and use the full brand where length allows. | 1 hour
SEO-17 | P2 | Confirm both phone numbers are active and intentional (sales line vs WhatsApp). Add both to Organization/LocalBusiness schema as separate ContactPoints with contactType. | If one is stale, replace it everywhere in one pass. | Schema lists all real numbers; no page shows a dead number. | 1 hour
SEO-18 | P2 | Strip app-shell artifacts ('Loading premium experience...', duplicate 'Mirai Tech' string) from the prerendered HTML output. | Exclude the loader element from the snapshot, or gate it behind JS so it never exists in static HTML. | curl of any page contains neither string. | 2 hours
SEO-19 | P2 | Verify hydration parity on every template incl. blog articles and /market-area: post-JS DOM keeps the same title, canonical, meta description, H1 and body content as the prerendered HTML. | Spot-check with Chrome DevTools (compare view-source vs rendered DOM) + GSC URL Inspection 'View crawled page' on 6 templates. | No template where hydration changes head tags or removes indexable content. | 0.5 day
SEO-20 | P2 | Add to the product template: breadcrumb trail (Home > Products > {Category} > {SKU}) and a 'Related Components' block of 4–6 same-category SKUs. | Related items can be same-category siblings by default; pairs well with BreadcrumbList schema from SEO-05. | Every product page exposes ≥5 internal links to other products/categories in prerendered HTML. | 1 day
SEO-21 | P2 | Run PageSpeed Insights (mobile) on homepage, IRFP4668 page, Bengaluru page. If LCP > 2.5s or INP > 200ms: defer/split the hydration bundle, preload the LCP element, subset fonts. | Prioritize JS reduction — the prerender already delivers content, so hydration can be lazy for below-the-fold widgets. | All three pages: LCP < 2.5s, INP < 200ms, CLS < 0.1 on mobile PSI. | 1–2 days if issues found

## 4. Redirect Map
# | Legacy URL (old PHP site) | Current behaviour (tested 16 Jul 2026) | Redirect Target (implement as single-hop 301) | Status
1 | https://www.miraitechnologies.net/brands.php | 301 → /about (confirmed live, but weak topical match; Google index entry still stale) | https://miraitechnologies.net/products | Re-point
2 | https://www.miraitechnologies.net/index.php | UNTESTED — pull actual status from GSC / curl | https://miraitechnologies.net/ | Fill & verify
3 | https://www.miraitechnologies.net/about.php | UNTESTED | https://miraitechnologies.net/about | Fill & verify
4 | https://www.miraitechnologies.net/products.php | UNTESTED | https://miraitechnologies.net/products | Fill & verify
5 | https://www.miraitechnologies.net/contact.php | UNTESTED | https://miraitechnologies.net/contact | Fill & verify
6 | (add every remaining .php URL found in GSC > Indexing > Pages and server access logs) | — | (closest-topic new URL — never blanket-redirect everything to the homepage) | To fill
Yellow cells = developer to fill/verify from Google Search Console and server logs before implementing. Rule: map each legacy URL to its closest-topic new page; single 301 hop; never chain through www or http.

## 5. Metadata Fixes
Page / Template | Element | Current (live 16 Jul 2026) | Problem | Proposed
Homepage | H1 | Buy Electronic Components Online India ¦ Mirai Technologies | H1 duplicates title tag verbatim incl. pipe + brand | Buy Genuine Electronic Components Online in India
/about | H1 | About Mirai Technologies ¦ Authorized Semiconductor Distributor | Same H1=title bug | About Mirai Technologies — Authorized Semiconductor Distributor Since 1999
Product template (ex: IRFP4668) | Title | IRFP4668 – N-ch MOSFET, 200V, 130A, Rds ¦ Buy India | Truncated mid-spec ('Rds' cut); 'Buy India' reads broken | IRFP4668 N-Channel MOSFET 200V 130A – Buy Online India ¦ Mirai Technologies (drop brand if >60 chars)
Product template (ex: IRFP4668) | Meta description | Buy IRFP4668 from Mirai Technologies Mumbai. N-ch MOSFET, 200V, 130A, Rds(on)=3.. ₹195/pc. Authorized distributor. Fast pan-India delivery. | Truncated mid-value 'Rds(on)=3..' | Buy IRFP4668 N-channel MOSFET (200V, 130A, TO-247AC) at ₹195/pc from Mirai Technologies, Mumbai. Authorized distributor since 1999. GST invoice, pan-India delivery.
City template (ex: Bengaluru) | Title | Component Distributor in Bengaluru ¦ Mirai Tech | Drops 'Electronic' (the target keyword head) + inconsistent brand 'Mirai Tech' | Electronic Component Distributor in Bengaluru ¦ Mirai Technologies
City template (ex: Bengaluru) | Meta description | Authorised distributor of Power MOSFETs, IGBTs, ICs & semiconductors in Bengaluru. Genuine parts, fast delivery. Call +91 93213 98188 or email sales@miraitec... | Truncated mid-email | Authorised distributor of Power MOSFETs, IGBTs, ICs & semiconductors in Bengaluru. Genuine, factory-traceable parts with GST invoice and fast pan-India delivery. Call +91 93213 98188.
All templates | Meta keywords | Identical boilerplate keyword string on every page | Obsolete tag; identical site-wide | Remove the tag entirely
Rule for generator | Title/description logic | Hard character truncation mid-token | Breaks words, values, emails | Truncate on word boundaries only (title ≤60 chars, description ≤155); never truncate inside an email/number/spec; prefer constructing from structured fields over truncating

## 6. Schema Checklist
Template | Required JSON-LD Type(s) | Key Fields (source of data already on page) | Placement Rule | Validation Step | Status
All pages | Organization + WebSite | name: Mirai Technologies; url; logo; foundingDate: 1999; address (Mumbai); contactPoint: both phone numbers + REAL email (bypasses Cloudflare obfuscation — see SEO-12); sameAs (IndiaMART/LinkedIn if any) | In prerendered <head>, once per page | Rich Results Test + Schema.org validator: 0 errors | To do
Product detail | Product + Offer (+ FAQPage + BreadcrumbList) | name: part no. + description; mpn: part number; brand: manufacturer (e.g. Infineon); offers: price (195), priceCurrency: INR, availability: InStock, seller: Organization; eligibleQuantity for MOQ 5. All values already printed in page body. | In prerendered <head>; price/stock in schema must match visible values exactly | Rich Results Test shows Product rich result preview with price + stock | To do
Product + city pages | FAQPage | Mark up the exact Q/A pairs already rendered on the page (3 FAQs per product, 5 per city page). Do not invent new Q/As in schema that aren't visible. | Schema Q/A text must match on-page text | Rich Results Test detects FAQ items = number of visible FAQs | To do
All pages | BreadcrumbList | Home > Products > {Category} > {SKU} for products; Home > Market Area > {City} for city pages | Requires visible breadcrumb UI too (SEO-20) | Breadcrumb rich result renders in test | To do
Blog articles | BlogPosting | headline, author (Person, from SEO-14), datePublished, dateModified, publisher: Organization, image | Article template head | 0 errors; article eligible for Top Stories-style display | To do
Contact + market-area | LocalBusiness | Full NAP: Mumbai address, geo, openingHours (Mon–Sat 9:30–18:30 per city page copy), telephone (both), email (real) | Prerendered head | LocalBusiness passes validation with real email visible in JSON | To do
CRITICAL NOTE | — | Static HTML fetch strips <script> tags, so this audit could NOT confirm whether any schema already exists. Before building, run each template URL through https://search.google.com/test/rich-results — if schema exists but is injected client-side after hydration, move it into the prerendered HTML (standing SSR requirement). | — | — | Verify first

## 7. Verification Tasks
# | Task | How to Check | Expected Result | Owner | Status
1 | robots.txt exists & correct | Open https://miraitechnologies.net/robots.txt; check GSC robots report | 200 OK; Sitemap: line present; Disallow: /cdn-cgi/; nothing important blocked | Developer | Open
2 | XML sitemap complete & submitted | Open /sitemap.xml; count URLs vs live page inventory (~130+); GSC > Sitemaps | All canonical URLs present, 0 errors in GSC | Developer | Open
3 | Host redirects (all 4 variants) | curl -IL on http://, http://www, https://www + 3 paths each | Single-hop 301 to https non-www every time | Developer | Open
4 | Full legacy .php URL inventory | GSC > Indexing > Pages (both www and non-www properties!) + server access logs; also Google 'site:miraitechnologies.net inurl:php' | Complete list pasted into Sheet 4 with targets | Developer | Open
5 | Add/verify BOTH GSC properties | Ensure Domain property (covers www + non-www) is verified, not just URL-prefix | Domain property active; legacy www data visible | Akshat | Open
6 | Existing schema check per template | Rich Results Test on: homepage, /products, product page, city page, blog article, /market-area | Documented: which schema exists today, and whether it's in prerendered HTML or JS-injected | Developer | Open
7 | Hydration parity spot-check | view-source vs rendered DOM on 6 templates; GSC URL Inspection 'View crawled page' | Head tags + content identical pre/post hydration | Developer | Open
8 | Blog article + market-area prerender | curl a blog article URL and /market-area; confirm full content in raw HTML | Same prerender quality as sampled pages | Developer | Open
9 | Core Web Vitals baseline | PageSpeed Insights mobile: homepage, IRFP4668, Bengaluru city page | LCP<2.5s, INP<200ms, CLS<0.1 — else SEO-21 work triggers | Developer | Open
10 | Image alt text & formats | Inspect product/category templates for img alt attributes, WebP, lazy loading | All content images have descriptive alts; modern formats | Developer | Open
11 | Phone numbers active | Call/WhatsApp both numbers | Both live, purposes documented → feed schema (SEO-17) | Akshat | Open
12 | Post-fix indexation monitoring | Weekly: GSC indexed-page count + site: check on www | Indexed count climbing toward full inventory; www legacy entries gone in 4–6 weeks | Akshat | Open